## Sheet1
Week | Feature/Deliverable | Difficulty (Hard/Medium/Easy) | Importance (Must Have/Nice to Have)
1 | Data exploration | medium | must have
1 | UI design | easy | must have
2 | build model | hard | must have
3 | test model | hard | must have
4 | stakeholder onboarding | medium | must have
5 | model deployment | medium | must have
6 | UI delivery | medium | must have